## Sheet1
Index | Risk Description | Evaluation | Responsible Party | Probability | Impact | Risk Factor | Control Measures | Response Measures | Associated User Stories
1 | Loss of data due to hardware failure | Lost data, and lost time due to need to replace it | Devs | 1 | 5 | 5 | Use cloud resources with redundancy to store all data. | Clone data from backup
2 | Data wrongly stored/alterd due to user error | Site reliability, comprehensiveness is damaged, leading to fewer users | Users/Devs | 2 | 3 | 6 | Ensure user documentation is complete and accurate | Re-enter data if it is locally available
3 | Loss/corruption of data due to software failure | All data is lost and people stop using the site | Devs | 2 | 5 | 10 | Ensure there is a back-up of the all data. Ensure high test coverage before app goes live. | Clone all data from backup
4 | Incorrect data added to db by a user | App becomes unreliable in terms of the information it holds and puts users off | devs/users | 2 | 3 | 6 | Could limit who was able to alter data by introducing a trusted user system | Regularly review information against trusted sources to ensure reliability
5 | User accidentally deletes data | Has to be re-entered to the db, could potentially result in loss of data if original source not available. | devs/users | 3 | 3 | 9 | Add an undo button so that the data can be re-input into the db without further problems | Re-enter data if it is locally available